|  |  |  |
| --- | --- | --- |
| CityofSavannah_Logo**Purchasing Summary** | | |
| **Event #**7197 | **Title:** Bryan Street Parking Garage Spall Repairs | **Cost:** $28,433.41 |
| **Type of Procurement:** Bid | **Annual Contract  Annual Maintenance Agreement** | **One Time Purchase** |
| **Contract Term (If Applicable)**  N/A | | |
| **LDBE (If Applicable)**  This event had a 20% LDBE goal. The recommended proposer submitted DBE participation at the subcontractor level in the amount of 20% using Visionary Services (10%) and MPW Construction (10%). | | |
| **Matrix (If Applicable)**  N/A | | |
| **Notes** | | |
| Recommend approval of a Final Project Closeout Amendment in the amount of $28,433.41 to Restocon Construction Company for additional work performed as part of the Spall Repairs at the Bryan St. Garage.  The original contract for this project involved repairing water damage caused by leaks from the garage deck above, including substantial concrete spalling repair, barrier cable replacement and coating of top floor of garage.  The amendment is required due to additional scope of services which included the repair of unforeseen spalling and replacement of additional barrier cables.  The original contract was bid and approved by City Council on February 1, 2018 in the amount of $359,860.  The total contract amount to date including this modification is $388,293.41.  L.B. Restocon Construction Company (Tampa, FL)(D)                                             $28,433.41  (D) indicates non-local, non DBE owned business | | |