## Master Compilation
# | Priority | Consultant's Recommendation(s) | Agree or Disagree | Responsive Actions | Responsible Parties | Begin Implementation | Complete Implementation
IMPLEMENTATION
Customer Service
1 | High | Replace single head meters with digital meters capable of accepting all major credit cards, smart cards, and mobile payments | Agree | Contract with current digital meter company is ready to move forward with Council approval. Estimated Cost: $2 million | Mobility and Parking | One Month | 6 months
2 | High | Establish automatic warnings for customers on a first offense | Agree | System is ready to carry out this recommendation | Mobility and Parking | One month | One Month
3 | Medium | Prioritize lower floors in garages for visitors | Agree | This would be phased in over the 5 garages within the system | Mobility and Parking | Two Months | One year
4 | High | Remove time zones in metered areas | Agree | Would be enacted with the installation of digital meters and new pricing at the beginning of 2018 | Mobility and Parking | Six Months | One year
| Medium | Investigate way finding systems for on and off street | Agree | On Street wayfinding would require implementation of digital meters. Off Street wayfinding would become standard in any new facility built. Currently investigating systems for current garages | Mobility and Parking | On Going | Two Years
5 | Medium | Implement mobile payments to parking meters | Agree | Passport mobile app is currently in beta testing on the street. | Mobility and Parking | Already occurring | Three Months
Pricing and Timing
6 | High | Extend meters times to time periods that need turnover for customers/visitors/residents (10 pm) | Agree in part | Based off of feedback in sessions, final staff recommendation is 8 pm. This was based on concerns raised by workers. Would be enacted with the installation of digital meters and new pricing at the beginning of 2018. Will also consider extension of enforcement times beyond 8pm in residential dominant areas. | Mobility and Parking | Six Months | One year
| High | Establish simplified times zones in residential dominated areas to protect resident parking | Agree | Zones would be implemented | Mobility and Parking | Six Months | Eight Months
| Medium | Establish regulations and exemptions for special/limited use permits (i.e.. Special events, houses of worship) | Agree | Meeting will take place with stakeholders in the next month | Mobility and Parking | One Month | Eight Months
7 | High | Extend meter enforcement into Saturday to promote turnover | Agree | Would be enacted with the installation of digital meters and new pricing at the beginning of 2018. Will also consider meter enforcement on Sunday starting in the afternoon | Mobility and Parking | One month | Nine Months
Alternative Transportation
8 | High | Promote alternative forms of transportation that encourage applicable users to help reduce parking demand in high use areas | Agree | Mobility and Parking is actively participating in programs designed to promote alternative transportation with plans for expansion | • Mobility and Parking • Chatham Area Transit • Savannah Area Mobility Management Board | Ongoing | One year
9 | High | Simplify and enhance the current circulator shuttles for users | Agree | Draft route has been created by Chatham Area Transit. CAT is developing future use agreement for city approval | • Chatham Area Transit • Mobility and Parking | On Going | Six Months
10 | Medium | Expand bike share program | Agree | City is assisting Chatham Area Transit in expansion of the program by acting as the local match. The City would operate the larger program in partnership with CAT. | • Chatham Area Transit • Mobility and Parking | On Going | One Year
| High | Expand bicycle routes where possible for users into and out of downtown | Agree | Currently working with engineers on expansion of bicycle facilities on Liberty/Wheaton. Final design is subject to staff/council approval. Also contributing to completion of Truman Linear Trail | • Mobility and Parking • Traffic Engineering • Sustainability Office | On-Going | Three Years
11 | High | Re-purpose existing analyst position in mobility and parking to focus on transportation/mobility | Agree | Position does exist and is vacant. | • Mobility and Parking • Human Resources | One Month | Three Months
12 | New Parking Facilities and Zoning
13 | Low | Promote new facilities in conjunction with positive peripheral downtown development | Agree | Ongoing discussions with developers. Will also incorporate in employee/worker parking | • Mobility and Parking • Development Services | Ongoing | Ongoing
14 | High | Allow payments in lieu of parking for development types that the city is promoting | Agree | Policy is being developed in conjunction with new zoning plan | • Development Services • Metropolitan Planning Commission • Mobility and Parking | Three Months | Six Months
15 | Medium | Allow for on street spaces to be considered in zoning requirements | Agree in part | Agree with this recommendation as long as the on street parking is regulated (i.e.. meters or time zones) | • Mobility and Parking • Development Services • Metropolitan Planning Commission | Ongoing | Eight Months
| Low | Allow for transportation connections to be considered in parking requirements | Agree | This has been applied in some variances that have been granted. Would be further recognized in the new zoning plan | • Mobility and Parking • Development Services • Metropolitan Planning Commission | Ongoing | Eight Months
16 |  |  |  | Research and Follow up
17 | High | Maintain program to continually conduct occupancy studies in order to determine the success of the proposed changes | Agree | Occupancy studies currently occurring in areas downtown as a follow up to the parking study | Mobility and Parking | Ongoing | Ongoing
18 | Medium | Establish a goal that regulated parking areas should be 70%-85% occupied as an ideal use | Agree | Occupancy studies currently occurring in areas downtown as a follow up to the parking study | Mobility and Parking | Currently in Effect | On
| High | Present applicable ordinances to City Council | Agree | Applicable ordinances are in development | • Mobility and Parking • City Attorney Office | Ongoing | Eight Months
19 | Medium | Establish system to address parking issues quickly by giving Mobility and Parking the ability to adjust rates and zones administratively | Agree | Policy is being developed as a part of proposed ordinance changes later this year | Mobility and Parking | Ongoing | Eight Months