## Sheet1
| RFI-001 | Column Locations at Entry Porch | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor. |  | Match RFI-013
| RFI-002 | Distance and Location of Beams | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
| RFI-003 | Moment Connection Detail | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
| RFI-005 | Perimeter Angle Use on Corners | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
| RFI-012 | Coping on Corners with Moment Connections | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
| RFI-013 | Masonry & Precast Support Steel at Entry Porch | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
| RFI-016 | Bus Canopy Welds and Connections | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
| RFI-010 | Catwalk Bracing Elevation | Structural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
| RFI-023 | Door Hardware Schedule Conflicts | Architectural | 1. Coordination/clarity due to unclear design/design error/omission. Supplemental information provided to Contractor.
Savannah Jumbo GA/FIS
Project Close Out Reconciliation
UPDATED 4/16/2020
RFI
Date | RFI | Description | Discipline | Disposition | Remarks
[6 empty] | AE | hrs | Admin | hrs | Jr AE | hrs | Total Labor | Total Expenses
2019-01-24 | RFI-143 | Generator Orientation and Pad Location | Mechanical, Electrical | 2. Coordination/clarity due to Contractor error. RS&H provided suggested solution or reviewed Contractor proposed solution. |  | 232 | 1 | 76 | 1 | 186 | 2 | 680
2019-06-28 | RFI-163 | Data Network Switches Clarfications | Technology | 4. The switch as specified was accepted by the Owner and provided by the Contractor. | The Contractor has submitted a statement. Can you reply and ask the Contractor to resubmit with a request for information and not a statement. Thank you. | 336 | 1 | 76 | 1 | 190 | 2 | 792
Total RFI | [11 empty] | 1472
SUBMITTAL
Date | Submital | Description | Discipline | Disposition | Remarks
[6 empty] | AE |  | Admin |  | JR AE
39 | Submittals reviewed in 2019
28 | RFI Either contactor error, review of contractor alternate proposal or CBP directed change
RE-SUBMITALS
Date | Submital | Description | Discipline | Disposition | Remarks
[6 empty] | Sr A/E | hrs | Admin | hrs | Jr A/E | hrs | Total Labor | Total Expenses
2019-02-25 | 06 41 16-02R1 | podiums | ARCH | CBP reivew delayed return of submittal |  | 141 | 12 | 76 | 1 | 79 | 0 | 1768
2019-02-14 | 08 14 16-02R2 | wood doors | ARCH |  |  | 141 | 2 | 76 | 1 | 79 | 0 | 358
2019-01-25 | 08 42 13-01R1 | aluminum doors | ARCH |  |  | 141 | 4 | 76 | 1 | 79 | 0 | 640
2019-02-21 | 08 80 00-01R1 | glazing | ARCH |  |  | 141 | 2 | 76 | 1 | 79 | 0 | 358
2019-04-16 | 09 24 00-01R1 | stucco | ARCH |  |  | 141 | 1 | 76 | 1 | 79 | 3 | 454
2019-02-11 | 09 67 23-01R1 | resinous flooring | ARCH |  |  | 141 | 1 | 76 | 1 | 79 | 0 | 217
2019-04-16 | 10 14 23.13-01R1 | signange | ARCH | CBP reivew delayed return of submittal |  | 141 | 6 | 76 | 1 | 79 | 6 | 1396
2019-06-10 | 10 14 23.13-01R2 | signange | ARCH | CBP reivew delayed return of submittal |  | 141 | 3 | 76 | 1 | 79 | 0 | 499
2019-05-01 | 10 22 19-01R1 | demountable partitions | ARCH |  |  | 141 | 2 | 76 | 1 | 79 | 1 | 437
2019-04-16 | 12 55 00-02R1 | detention furniture | ARCH | CBP reivew delayed return of submittal |  | 141 | 2 | 76 | 1 | 79 | 3 | 595
2019-03-21 | 23 31 13-01R1 | metal duct | MECH |  |  | 232 | 1.5 | 76 | 1 | 186 | 1.5 | 703
2019-01-22 | 26 09 43-01R2 | lighting controls | ELEC |  |  | 242 | 1 | 76 | 1 | 195 | 1 | 513
2019-02-13 | 26 09 43-01R3 | lighting controls | ELEC |  |  | 242 | 1 | 76 | 1 | 195 | 2 | 708
2019-01-09 | 26 32 13-01R3 | generator enclosure | ELEC |  |  | 242 | 0 | 76 | 1 | 195 | 2 | 466
2019-01-17 | 26 51 00-03R1 | lighting fixtures | ELEC |  |  | 242 | 0 | 76 | 1 | 195 | 2 | 466
2019-01-22 | 26 51 00-03R2 | lighting fixtures | ELEC |  |  | 242 | 3 | 76 | 1 | 195 | 1 | 997
2019-02-13 | 27 05 00-01R2 | comm equip | TECH |  |  | 336 | 1 | 76 | 1 | 190 | 1 | 602
2019-02-25 | 28 13 00-02R1 | access controls | TECH |  |  | 336 | 3 | 76 | 1 | 190 | 2 | 1464
2019-02-13 | 28 23 00-01R1 | video surveilance | TECH |  |  | 336 | 1 | 76 | 1 | 190 | 1 | 602
2019-02-21 | 28 23 00-01R2 | video surveilance | TECH |  |  | 336 | 1 | 76 | 1 | 190 | 1 | 602
2019-01-17 | L131-01R2 | apron lighting | CIVIL ELEC |  |  | 216 | 0 | 76 | 1 | 95 | 2 | 266
2019-01-23 | L131-01R3 | apron lighting | CIVIL ELEC |  |  | 216 | 0 | 76 | 1 | 95 | 1 | 171
2019-02-11 | L131-03R1 | site lighting | CIVIL ELEC |  |  | 216 | 1 | 76 | 1 | 95 | 2 | 482
Total Re-Submittal | [11 empty] | 14764
EXPENSE/SITE VISIT/PUNCH LIST/MEETING/CALL
Date | Submital | Description | Discipline | Disposition | Remarks
[6 empty] | Sr A/E | hrs | Admin | hrs | Jr A/E | hrs | Total Labor | Total Expense
Expense
5/1/2019 | m weibe reed | parking |  | 0 | 0 | [7 empty] | 31.55
5/1/2019 | m weibe reed | car |  | 0 | 0 | [7 empty] | 46
5/1/2019 | m weibe reed | meal | [10 empty] | 18
5/1/2019 | m weibe reed | gas | [10 empty] | 32
2019-06-24 | m weibe reed | car | [10 empty] | 137
2019-07-09 | m weibe reed | car | [10 empty] | 137
2019-09-12 | m weibe reed | meal | [10 empty] | 110
2019-09-12 | m weibe reed | mileage | [10 empty] | 146
2019-11-26 | m weibe reed | meal |  | 0 | 0 | [7 empty] | 43
2019-11-26 | m weibe reed | mileage | [10 empty] | 146
2020-02-12 | dale stubbs | airfare | [10 empty] | 597
2020-02-12 | dale stubbs | meal | [10 empty] | 9
2020-02-12 | dale stubbs | meal | [10 empty] | 17
2020-02-14 | dale stubbs | mileage | [10 empty] | 12
Total Expenses | [12 empty] | 1481.55
[6 empty] | Sr A/E | hrs | Admin | hrs | Jr A/E | hrs | Total Labor | Total Expenses
Site Visit
2019-05-01 | m weibe reed | site visit |  | hrs include travel time |  | 141 | 8 |  |  |  |  | 1128
2019-06-06 | dale stubbs | site visit |  | hrs include travel time |  | 347 | 8 |  |  |  |  | 2776
2020-06-24 | m weibe reed | owner requested site visit-see email with this date |  | hrs include travel time |  | 141 | 8 |  |  |  |  | 1128
2019-07-09 | m weibe reed | site visit |  | hrs include travel time |  | 141 | 8 |  |  |  |  | 1128
2019-09-12 | m weibe reed | site visit |  | hrs include travel time |  | 141 | 8 |  |  |  |  | 1128
2019-11-26 | m weibe reed | site visit |  | hrs include travel time |  | 141 | 8 |  |  |  |  | 1128
7/11/19 Substantial Completion Punch List | [11 empty] | 8416
8/5/19 Final Completion
[6 empty] | Sr A/E | hrs | Admin | hrs | Jr A/E | hrs | Total Labor | Total Expenses
punch list | team member
2019-07-22 | m weibe reed |  |  |  |  | 141 | 8 | 0 | 0 |  |  | 1128 |  | m weibe reed, r fletcher,
| robert fletcher |  |  |  |  | 213 | 8 |  |  |  |  | 1704
Total Expenses | [11 empty] | 2832
[6 empty] | Sr A/E | hrs | Admin | hrs | Jr A/E | hrs | Total Labor | Total Expenses
Meeting/Call
2019-01-14 | [5 empty] | 141 | 2 |  |  |  |  | 282
2019-02-07 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-02-11 | [5 empty] | 141 | 1 |  |  |  |  | 141
2019-02-21 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-02-28 | [5 empty] | 141 | 3 |  |  |  |  | 423
2019-03-03 | [5 empty] | 141 | 2 |  |  |  |  | 282
2019-03-04 | [5 empty] | 141 | 2 |  |  |  |  | 282
2019-03-06 | [5 empty] | 141 | 2.5 |  |  |  |  | 352.5
3/7/2019 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-03-08 | [5 empty] | 141 | 2 |  |  |  |  | 282
2019-03-15 |  |  |  |  | 0 | 141 | 1 |  |  |  |  | 141
2019-03-18 | [5 empty] | 141 | 3 |  |  |  |  | 423
2019-03-19 | [5 empty] | 141 | 1 |  |  |  |  | 141
2019-03-20 | [5 empty] | 141 | 2 |  |  |  |  | 282
2019-03-21 |  |  |  |  | 0 | 141 | 1 |  |  |  |  | 141
2019-03-25 | [5 empty] | 141 | 2 |  |  |  |  | 282
2019-04-04 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-04-16 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-04-17 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-04-18 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-04-19 |  |  |  |  | 0 | 141 | 1 |  |  |  |  | 141
2019-05-02 |  |  |  |  | 0 | 141 | 1.5 |  |  |  |  | 211.5
2019-05-31 | [5 empty] | 141 | 2 |  |  |  |  | 282
6/14/2019 |  |  |  |  | 0 | 141 | 2 |  |  |  |  | 282
2019-09-12 | [5 empty] | 141 | 3 |  |  |  |  | 423
Total Non-Regular Site Visits in CY 2019/Punch Lists in Excess of One/Expenses | [11 empty] | 6768
Coordination with CBP on Post Design Add/Changed Items
podiums (primary and secondary) coordination | [5 empty] | Sr A/E | hrs | Durations |  |  |  | Total Labor | Total Costs
20 email | [5 empty] | 141 | 20 | 1 hr ea |  |  |  | 2820
6 revisoin sketches | [5 empty] | 141 | 12 | 2 hr ea |  |  |  | 1692
2 color selelction boards | [5 empty] | 141 | 4 | 2 hr ea |  |  |  | 564
23 phone calls | [5 empty] | 141 | 23 | 1 hr ea |  |  |  | 3243
furniture/equipment coordination
7 email | [5 empty] | 141 | 6 | 1 hr ea |  |  |  | 846
5 phone calls | [5 empty] | 141 | 5 | 1 hr ea |  |  |  | 705
signange coordiation
3 email | [5 empty] | 141 | 3 | 1 hr ea |  |  |  | 423
5 phone calls | [5 empty] | 141 | 5 | 1 hr ea |  |  |  | 705
door frames/doors coordination
5 emails | [5 empty] | 141 | 5 | 1 hr ea |  |  |  | 705
3 phone calls | [5 empty] | 141 | 6 | 2 hr ea |  |  |  | 846
combi flush valve coordination
3 emails | [5 empty] | 141 | 3 | 1 hr ea |  |  |  | 423
5 phone calls | [5 empty] | 141 | 5 | 1 hr ea |  |  |  | 705
cameras added and moved
2 emails | [5 empty] | 141 | 2 | 1 hr ea |  |  |  | 282
3 phone calls | [5 empty] | 141 | 6 | 2 hr ea |  |  |  | 846
DIRTT wall coordination
3 emails | [5 empty] | 141 | 3 | 1 hr ea |  |  |  | 423
4 phone calls | [5 empty] | 141 | 4 | 1 hr ea |  |  |  | 564
Total CBP Coordination Time | [11 empty] | 15792
TOTALS: | [12 empty] | 51525.55

## Sheet2
2019-09-11 | punch list | Weibe-Reed, Marjorie |  | 141 | 1 | 0 | 141
2019-09-12 | punch list | Fletcher, Robert |  | 336 | 2 | 0 | 672
2019-09-12 | punch list reivew w cbp, SAC meeting, site visit | Weibe-Reed, Marjorie |  | 141 | 3 | 0 | 423
2019-10-10 | punch list | Weibe-Reed, Marjorie |  | 141 | 2 | 0 | 282
2019-10-11 | SAV FIS Punch List - Access Controls and door hardware | Fletcher, Robert |  | 336 | 1.5 | 0 | 504
2019-10-11 | punch list | Weibe-Reed, Marjorie |  | 141 | 2 | 0 | 282
2019-10-14 | Structural Observation Letter | Jackson, Aaron |  | 336 | 0.25 | 0 | 84
2019-10-14 | punch list | Weibe-Reed, Marjorie |  | 141 | 2 | 0 | 282
2019-10-15 | punch list | Weibe-Reed, Marjorie |  | 141 | 2 | 0 | 282
2019-10-16 | punch list | Weibe-Reed, Marjorie |  | 141 | 2 | 0 | 282
2019-10-17 | punch list | Weibe-Reed, Marjorie |  | 141 | 2 | 0 | 282
2019-10-23 | punch list update | Weibe-Reed, Marjorie |  | 141 | 2 | 0 | 282
2019-11-26 | site visit, pco's and pucnh list | Weibe-Reed, Marjorie |  | 141 | 6 | 0 | 846
2019-01-16 |  | Weibe-Reed, Marjorie | 0 | 141 | 4 |  | 564
2019-06-24 | owner requested site visit | Weibe-Reed, Marjorie | 0 | 141 | 8 |  | 1128
2019-05-01 | sac & RFI 153 | Weibe-Reed, Marjorie | 0 | 141 | 8 |  | 1128
2019-04-03 | oac/site visit | Weibe-Reed, Marjorie | 0 | 141 | 7 |  | 987
2019-02-06 | oac/change orders/submittals/site visit | Weibe-Reed, Marjorie | 0 | 141 | 8 |  | 1128
2019-08-05 | site visit | Weibe-Reed, Marjorie |  | 141 | 8 |  | 1128
2019-02-15 | site visit | Weibe-Reed, Marjorie |  | 141 | 8 |  | 1128
2019-02-05 | site visit | Weibe-Reed, Marjorie |  | 141 | 8 |  | 1128