## Slide 1: SAVANNAH PUBLIC ART MASTER PLAN
City Council Update
March 13, 2025

## Slide 2: TIMELINE
September
October
November
December
January
February
March
April
May
June
July
August
PHASE 1:
MOBILIZATION
PHASE 2:
COMMUNITY DIALOGUE & ENGAGEMENT
PHASE 3:
SYNTHESIZE IDEAS & DEFINE STRATEGY
PHASE 4:
INITIAL RECOMMENDATIONS
PHASE 5:
FINAL REVIEW & RECOMMENDATION

## Slide 3: COMPLETED PROJECT TASKS
Project Mobilization
  Conducted a 3-day discovery visit in November
  Developed a project brand, website, and collateral
  Hosted first Steering Committee meeting
Completed Community Engagement
  Visited for Engagement kick off in February
  Released a public survey, received 425+ responses
  Public press event with performances and remarks from City leadership
  Completed 25 Stakeholder one-on-one conversations
  Hosted 6 district-specific Focus Groups and 6 Community Workshops - engaged over 100 participants combined
  Hosted second Steering Committee meeting
Notes: Amanda

## Slide 4: NEXT STEPS
Develop a Listening Summary
  Analyze survey findings
  Summarize community feedback, identify the City’s unique characteristics and needs
  Develop a vision statement and guiding principles for the Plan
  Third Steering Committee meeting
Evaluate Assets
  Understand current collection
  Define the goals and objectives of the Savannah Public Art Master Plan
Begin Writing Recommendations
  Locations for public art
  Public art project ideas
  Public art themes
  Administrative and process recommendations
  Fourth Steering Committee Meeting
Final Plan Review
Presentation
Notes: Amanda

## Slide 5
Take the Public Art Survey!