## Slide 1
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
CITY OF SAVANNAH CAPITAL PROJECTS
UPDATE
CITY COUNCIL WORKSHOP
JUNE 8, 2023

## Slide 2: CAPITAL PROJECT
A capital project is a long-term capital-intensive investment project with a purpose to build upon, add to, or improve a capital asset.
A capital project can be new construction, renovation, or a replacement project for an existing facility or facilities.
Project costs can include the cost of land, planning, engineering, architecture, construction, and other services needed to complete the project.
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Hudson Hill Community Center

## Slide 3: CAPITAL IMPROVEMENT PROGRAM OVERVIEW – Q1 2023
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
288 Total Projects Citywide
25 Project Managers Citywide
$444,456,764
Total Budget of All Capital Projects
Chart: 
| Civic Center | Cemetry | Community Development | Drainage | Holding accounts | Other | Parks & Recreation | Public Building | Sanitation | Sewer | Squares & Monuments | Street | Traffic | Water | I&D Water Plant
# of Projects | 2 | 6 | 14 | 17 | 11 | 33 | 19 | 42 | 4 | 38 | 11 | 20 | 22 | 43 | 1
Appropriated Budget To Date | -305644.94 | -1153565.19 | -13861581.09 | -93245405.73 | -36032614.19 | -23799781.05 | -22522852.26 | -43171483.68 | -2597393.45 | -73158350.72 | -187431.41 | -20804914.29 | -22412674.3 | -81915609.08 | -268060.96
Expenditures To Date | 34351.55 | 153448.57 | 800187.78 | 1007390.54 | 0 | 1392390.95 | 2113550.56 | 941653.77 | 71608.62 | 3403710.53 | 182980.43 | 1666360.09 | 72474.5 | 310446.98 | 0
Open Purchase Orders To Date | 36031.95 | 31785.58 | 1920091.07 | 1401983.1 | 0 | 8108552.68 | 2991567.6 | 10964368.03 | 1095867.69 | 2588551.14 | 60383.47 | 421885.35 | 1946127.26 | 1214403.81 | 980.83
Project Balance to Date | -271293.39 | -1000116.62 | -13061393.31 | -92345683.01 | -36032614.19 | -22407390.1 | -20409301.7 | -42229829.91 | -2525784.83 | -69754640.19 | -4090217.82 | -19138554.2 | -22340199.8 | -81605162.1 | -268060.96

## Slide 4: PROJECT MANAGERS ACROSS THE CITY
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Chart: 
| Community Services | Government Operation | Captial Project | Park & Tree | Parking Services | Transportation | Urban planning & design | Water Resources
Project Managers | 1 | 1 | 5 | 3 | 1 | 2 | 1 | 11

## Slide 5: OFFICE OF CAPITAL PROJECTS MANAGEMENT
Senior Director
Cristy Lawrence, P.E.
Construction Inspector
Jim Wood
Contract Coordinator
Amber Williams
4 Capital Project Managers
Leif Blomberg
Carol Moon
Dan Reel
Byron Stiles
Senior Capital Project Manager
Doug Patten, P.E.
Senior Admin
Jenneida White
Capital Projects Liaison Philip Kalogitonas
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
5 Project Managers
49 Active Projects
$303,733,237
Total Project Budget

## Slide 6
Planning (Pre-design)
Design & Permitting
Pre-Construction
(Procurement)
Construction
Develop overall programming needs: who & what needs to go into facility
Community Engagement
Collect Site/Building Information
Develop Conceptual Cost Estimates
Procure Architect/Engineer/Design Consultant
Finalize Programming
Prepare Schematic Design
Prepare Final Design (Construction Documents)
Obtain Necessary Permits
Prepare bid documents
Advertise for Bid
Review & Evaluate Bids
Obtain Approval of Procurement by City Council
Execute Contract
Issue Notice to Proceed
Pre-Construction Meeting
Construction
Final Inspections
Occupancy
CAPITAL PROJECT ROADMAP

## Slide 7
9 Months
11-12 Months
4 Months
14-16 Months
Planning & Community Engagement
Design & Permitting & Continued Community Engagement
Procurement
Construction
TYPICAL FIRE STATION/COMMUNITY CENTER – Total Time to Complete = 3 – 3 ½ YEARS*
TYPICAL BUILDING RENOVATION – Total Time to Complete = 2 ½ – 3 ½ YEARS*
9 Months
9-15 Months
4 Months
9-15 Months
TYPICAL PARK IMPROVEMENT – Total Time to Complete = 1 ½ – 2 ½ YEARS*
6-9 Months
4 Months
6-9 Months
3-6 Months
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
EXAMPLE CAPITAL PROJECT TIMELINES
*Note: When needed, Value Engineering typically adds 1-2 months
PROJECT PHASES:

## Slide 8
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
CAPITAL PROJECT TIMELINES – ACTIVE LARGE CONSTRUCTION PROJECTS
TODAY
Planning & Community Engagement
Design & Permitting & Continued Community Engagement
Procurement
Construction
PROJECT PHASES:
7 Months
Estimated Completion Q1 2024
Placentia Canal Drainage Improvements Phase 5 (Semken & LaRoche Ave Bridge Replacements)
19 Months
Lift Station #23 Upgrades
Estimated Completion Q4 2024
4 Months
3 Mos
6 Months
New Hampstead Temporary Joint Public Safety Facility (Highgate Blvd.)
Estimated Completion Summer 2024
15 Months
Police Headquarters Renovation
Estimated Completion Summer 2024

## Slide 9
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
CAPITAL PROJECT TIMELINES – ACTIVE LARGE CONSTRUCTION PROJECTS
TODAY
Planning & Community Engagement
Design & Permitting & Continued Community Engagement
Procurement
Construction
PROJECT PHASES:
4 Months
15 Months
Gamble Building Renovation:
6 Months
Estimated Completion Summer 2025
5 Months
18 Months
Truman Linear Trail Phase 2B:
Estimated Completion Summer 2025
2 ½ Years
DeLesseps Avenue Widening
Estimated Completion Q4 2025
4 Months
7 Months
2 Years
Springfield Canal Phase 1 Drainage Improvements (Wetland Park)
Estimated Completion Q2 2026

## Slide 10
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
CAPITAL PROJECT TIMELINES – ACTIVE LARGE CONSTRUCTION PROJECTS
TODAY
Planning & Community Engagement
Design & Permitting & Continued Community Engagement
Procurement
Construction
PROJECT PHASES:
2 Mos
4 Months
12 Months
19 Months
New Hampstead Permanent Joint Public Safety Facility (Little Neck Rd.)
Estimated Completion Q4 2026
4 Months
Procurement of Design
Procurement of Construction
2 Years
Casey South Phase 3 Drainage Improvements (Deep Tunnel) (Note: Funding must be identified prior to start of construction)
Estimated Completion Q2 2027
4 Months
Procurement of Design
14 Months
4 Months
Procurement of Construction
4 Months
9 Months
3 Years
Springfield Canal Phase 2 Drainage Improvements (Canal Walls)
Estimated Completion Q3 2027
4 Years
Casey South Phase 2-1 & 2-2 Drainage Improvements
Estimated Completion Q4 2027
4 Months

## Slide 11: TYPICAL PROJECT CHALLENGES
Weather delays
Unsuitable soils
  Geotechnical reports based on soil samples
Unknowns under the ground
  i.e. debris, utilities, abandoned storage tanks, environmental concerns (contamination)
Unknowns in existing buildings in renovation projects
  Asbestos/lead
  Mold
  Missing structural components
  Mechanical, electrical & plumbing systems
City-requested changes/additions to scope during design or construction

## Slide 12: Status of Special Purpose Local Option Sales Tax (SPLOST) Projects*
*Excluding SPLOST 7 (2020 – 2026)
SPLOST 1
(1985-1993)
SPLOST 2
(1993-1998)
SPLOST 3
(1998-2003)
SPLOST 4
(2003-2008)
SPLOST 5
(2008-2014)
SPLOST 6 (2014-2020)

## Slide 13: REMAINING SPLOST PROJECTS
SPLOST 4 2003-2008 STATUS
Stormwater Brick Line Replacement Ongoing
Springfield Drainage Improvements Under Construction
DeLesseps Avenue Widening Under Construction
W.W. Law Collection Archival Implementation
SPLOST 5 2008-2014 STATUS
37th Street Corridor Signal Improvement In Design (SS4A Grant)
Casey South Drainage Phase II Phase 1 Under Construction
Street Lighting Upgrade Ongoing

## Slide 14: REMAINING SPLOST PROJECTS
SPLOST 6 2014-2020 STATUS
Wireless/Fiber Infrastructure Conceptual/Planning
Atlantic Park Improvements Conceptual/Planning
Project DeRenne Design/Preconstruction
Wheelchair Access Ramps Under Construction
Coastal Heritage Society Improvements Under Construction
Highlands Park Phase 1 Under Construction
Drainage Box Rehabilitations Under Construction
Placentia Basin Drainage Improvements Under Construction
Pedestrian Wayfinding Signage Under Construction
Victory Drive Landscaping & Irrigation Under Construction

## Slide 15: FUTURE CAPITAL NEEDS
Municipal Space Needs
Public Safety
Drainage
Mobility/Transportation
Recreation

## Slide 16: PROJECTS COMPLETED IN 2020
*SPLOST Projects
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Highlands Drive Sign Repair
Bonaventure Cemetery Restroom Building
Crusader Center Basketball Resurfacing
Fire Dock Replacement
Cloverdale Sign Repair
Glynnwood
Sign
SPD Special Operations Storage Building – FEMA Repairs
Liberty Street Garage 5th Floor Structural Repairs
Recreational Dock Gangway Replacement
State Street Garage MPC Office Repairs
FEMA - Hurricane Matthew Repairs - Paulson Recreational Complex Roof Repair
Factors Walk - Barnard Ramp Repairs
Holly Heights Park Improvements
Colonial Cemetery Lighting
Eastern Wharf Dock Repair
Summerside Park
Robinson Garage Elevator Modernization
Alfred Street Culvert Extension
Bryan Street Garage Beam Spalling Repairs
Silverton Sign Demo
Fire Station Headquarters Chimney Repair
Twickenham Greenspace

## Slide 17: PROJECTS COMPLETED IN 2021
*SPLOST Projects
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Paradise Park Sign Insert Replacement
Mohawk Park
Jan Street Improvements
Highlands Fire Station
Ogeecheeton Park ADA Repair
3rd Floor City Hall Offices
Woodville-Sidewalk on Alfred Street between King Street and Lissner Street
Riverwalk Wharf Repairs
Police Memorial Trail Repairs
WW Law Center Roof Replacement
Floyd Adams Complex
Abercorn Creek Municipal Water Intake - FEMA - Hurricane Matthew Repairs

## Slide 18: PROJECTS COMPLETED IN 2022
*SPLOST Projects
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Waters Ave Streetscapes Phase III
Arena City Lot "Waterworks Lot Site Development"
Arena Pedestrian Bridge
Cedar Street Improvements Phase III
Arena Marquee Sign
Greenwich Cemetery Section 6 Expansion
Arena, Canal Bulkhead, & Force Main
Emergency Repair of Recreational Dock
Fernwood Bridge Deck Replacement
Sanitation Headquarters Renovation
Savannah Gardens Phase 3B Master Infrastructure
Arena Parking Garage
Factors Walk 316 E. Bay Street Stair Replacement
Truman Parkway and President Street Clearing and Fencing

## Slide 19: PROJECTS COMPLETED IN 2023 (TO DATE)
Joe Tribble Park Lake Repairs
Leedsgate Gazebo
Grant Center Gymnasium
Delaware Center Renovation
Riverwalk Extension
*SPLOST Projects
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Broughton Streetscapes Phase 1
Fleet Services Renovation – 8 Interchange Court
Waters Avenue Shopping Center Savannah Impact Program (SIP) Buildout
Fire Support/ Code Compliance Renovation
Stiles Avenue Phase 1

## Slide 20: PROJECTS TO BE COMPLETED IN 2023 BY YEAR END
Entrepreneurial Center Building Envelope Repairs
Fleet Maintenance Sallie Mood Roof Repairs
Fleet Maintenance Automatic Transfer Switch Replacement
Dundee Cottage Infrastructure
*SPLOST Projects
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Cultural Arts Center Atrium Rigging
Hudson Hill Community Center
Coastal Heritage Society Storehouse Roof Replacement
Highlands Park Phase 1
President Street Plant Freight Elevator Repair
IT Ring Generators
Municipal Archives Upgrades

## Slide 21: Capital Project Highlights

## Slide 22
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
HUDSON HILL COMMUNITY CENTER
Estimated Project Budget: $3.3 Million
Project Scope:
New 4,600 sq. ft. Community Center with classrooms, offices, a large assembly space with commercial kitchen, and increased parking
Estimated Project Schedule:
Completion Date – June 2023

## Slide 23
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Highlands Park Phase 1
Estimated Phase 1 Project Budget: $1.3 Million
Project Scope:
Phase 1 of the park is a half-mile walking trail and parking lot along the northside of the property, north of Basswood Drive
Highlands Park will be a planned 33-acre large regional park
Estimated Project Schedule:
Completion Date – June 2023

## Slide 24
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
Police Headquarters Renovations
Plaster deterioration and openings in wall
Window moisture damage containing rot
Window units causing
moisture accumulation and mildew
Estimated Project Budget: $8.5 Million
Project Scope:
Building envelope repairs include new windows, HVAC system, and exterior wall insulation.
Interior renovation includes updated office layout, new ceiling tile, paint, flooring, lighting upgrade to LED lights, and IT infrastructure.
Estimated Project Schedule:
Completion Date – Summer 2024

## Slide 25
City of Savannah / Office of Infrastructure & Development/ Office of Capital Projects Management
GAMBLE BUILDING RENOVATION
Estimated Project Costs:
Design $ 625,000
Construction $12,700,000
Other Project Costs $ 1,575,000
Scope:
Interior and exterior renovations including MEP systems, building structure, building envelope, ADA, and life safety improvements to create a modern office space for staff
Estimated Project Schedule:
Design Completion – Q3 2023
Start of Construction – Q1 2024
Completion – Summer 2025

## Slide 26: OFFICE OF CAPITAL PROJECTS MANAGEMENT
QUESTIONS?